## Sheet1
PartnerPortal - WorkOrder Flow |  | Projekt plan
Area: | Create incomming SOAP interface for SonWin Test Environment |  | Estimate in story points |  |  |  | Avg:
Task |  | Description | Best case | Reel | Worst case | Assigned to
Create SOAP WCF Service |  | Create a WCF Service Application in the existing PP GIT Repository | 3 | 3 | 5 | PAHEH
HttpS setup |  | Add httpS connection in the WCF service according to the configuration in the existing InstallationsBlanbket.dk interface | 3 | 8 | 8 | PAHEH
Configuration of service |  | Add configuration for the binding according to existing installations blanket service | 1 | 2 | 3 | PAHEH
Demo project |  | Expand UI demo project for consuming and calling real xms | 2 | 3 | 3 | PAHEH
Build configuration |  | Find out and make the build configuration for the service to be build in build env. (Info talk with someone) |  |  |  | JOHAN
Deployment |  | Deploy the service in the test environment (Ports, env setup) | 3 | 5 | 8 | PAHEH
Establish connection |  | Setup SonWin Server InstallationManagementElectricity Service for connecting with the new WFC service | 2 | 8 | 8 | PAHEH
|  | Estimation: | 14 | 29 | 35 |  | 29
Area: | Create outgoing SOAP API interface
Task |  | Description | Best case | Reel | Worst case | Assigned to
Create SOAP consumer |  | Create flow for communication from the Partner Portal in the WCF Service | 3 | 5 | 5 | PAHEH
Create SOAP consumer |  | Consume the client interface | 3 | 5 | 5 | PAHEH
Create SOAP consumer |  | Establish flow handling from A -> B | 5 | 8 | 8 | PAHEH
|  | Estimation: | 11 | 18 | 18 |  | 18
Area: | Create DTO Objects matching XML creation (IN = Incomming/OUT = Outgoing)
Task |  | Description | Best case | Reel | Worst case | Assigned to
Tilmelding 'Annullering' (IN/OUT) |  | Create the DTO entity for serializing to xml
Tilmelding 'Annullering' (IN/OUT) |  | Create autotest for ensuring that the generated xml will not be changed
Tilmelding 'Erstatning' (IN) |  | Create the DTO entity for serializing to xml
Tilmelding 'Erstatning' (IN) |  | Create autotest for ensuring that the generated xml will not be changed
Tilmelding ’Original’ (OUT) |  | Create the DTO entity for serializing to xml
Tilmelding ’Original’ (OUT) |  | Create autotest for ensuring that the generated xml will not be changed
Tilmelding og færdigmelding (OUT) |  | Create the DTO entity for serializing to xml
Tilmelding og færdigmelding (OUT) |  | Create autotest for ensuring that the generated xml will not be changed
Tilmelding og færdigmelding ’Erstatning’ (IN) |  | Create the DTO entity for serializing to xml
Tilmelding og færdigmelding ’Erstatning’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed
Anvisning, svar på ’Original’ (IN) |  | Create the DTO entity for serializing to xml
Anvisning, svar på ’Original’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed
Tilmelding afsluttet ’Original’ (IN) |  | Create the DTO entity for serializing to xml
Tilmelding afsluttet ’Original’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed
Afvisning af ’Tilmelding’ (IN) |  | Create the DTO entity for serializing to xml
Afvisning af ’Tilmelding’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed
Færdigmelding (OUT) |  | Create the DTO entity for serializing to xml
Færdigmelding (OUT) |  | Create autotest for ensuring that the generated xml will not be changed
Klar Til måler ’Original’ (OUT) |  | Create the DTO entity for serializing to xml
Klar Til måler ’Original’ (OUT) |  | Create autotest for ensuring that the generated xml will not be changed
SagsInfo (?) |  | Create the DTO entity for serializing to xml
SagsInfo (?) |  | Create autotest for ensuring that the generated xml will not be changed
|  | Estimation: | 0 | 0 | 0 |  | 0
Area: | Various tasks
Task |  | Description | Best case | Reel | Worst case | Assigned to
Datamodel exted |  | Extend the data model with XML codes (also in the database)
Real life xml data |  | Add functionality in SW inst service for dumping xml documentation for use in flow comparison |  |  |  | PAHEH
Form and data header to xml |  | Outgoing flow needs headers in the messages
Investigate |  | Shared entities in the XML documents, how to manage differentiating structures
Logging |  | Add logging functionality to the Soap interface
Versioning |  | Create versioning in the service
Investigate |  | Schematron in workorder? What are the needs and are there any? |  |  |  | PAHEH
IP whitelisting |  | Create DB table for configuration |  |  |  | JOHAN
IP Whitelisting |  | Create logic for checking IP address against saved addresse |  |  |  | PAHEH
IP whitelisting |  | Create UI for saving IP addresses for customer
Area: | Incomming
Task |  | Description | Best case | Reel | Worst case | Assigned to
Error messages |  | How to send/report errors?
Area: | Outgoing
Task |  | Description | Best case | Reel | Worst case | Assigned to
Deserialization |  | Add method for deserializing (Xml string to Entity) |  |  |  | JOHAN
Deserialization |  | Add Autotest for deserialization |  |  |  | JOHAN
Re-send (Handshake) |  | If the message is not incepted by the client, then the server should retry sending the message at a certain interval untill it does, but how?
Area: | Tests
Task |  | Description | Best case | Reel | Worst case | Assigned to
Auto tests |  | Add tests for the incomming flow
Auto tests |  | Add tests for the outgoing flow
Manual testing |  | Flow testing for the new installations flow
Manual testing |  | Flow testing for Expanding flow
Manual testing |  | Flow testiing for the Plombebrud flow
Area: | Documentation
Task |  | Description | Best case | Reel | Worst case | Assigned to
Documentation |  | Create external installation manual for customers to use when setting up/creating the clients in their end
Documentation |  | Create internal installation manual/trouble shooting guides for internal personnel
Documentation |  | Create developer documentation for flow/debugging/etc
Finde ud af:
Kø til resend, gemning etc.
Flow engine