## Sheet1
PartnerPortal - WorkOrder Flow |  | Projekt plan
Area: | Create incomming SOAP interface for SonWin Test Environment |  | Estimate in story points |  |  |  | JIRA Created | Avg: | Worst | SP JOHAN | SP PAHEH
Task |  | Description | Best case | Reel | Worst case | Assigned to
Create SOAP WCF Service |  | Create a WCF Service Application in the existing PP GIT Repository | 3 | 3 | 5 | PAHEH | x
HttpS setup |  | Add httpS connection in the WCF service according to the configuration in the existing InstallationsBlanbket.dk interface | 3 | 8 | 8 | PAHEH | x
Configuration of service |  | Add configuration for the binding according to existing installations blanket service | 1 | 2 | 3 | PAHEH | x
Demo project |  | Expand UI demo project for consuming and calling real xms | 2 | 8 | 3 | PAHEH | x
Build configuration |  | Find out and make the build configuration for the service to be build in build env. (Info talk with someone) | 2 | 3 | 3 | JOHAN | x
Deployment |  | Deploy the service in the test environment (Ports, env setup) | 8 | 8 | 13 | PAHEH | x
Establish connection |  | Setup SonWin Server InstallationManagementElectricity Service for connecting with the new WFC service | 2 | 8 | 8 | PAHEH | x
|  | Estimation: | 21 | 40 | 43 |  |  | 40 | 43 | 3 | 29
Area: | Create outgoing SOAP API interface
Task |  | Description | Best case | Reel | Worst case | Assigned to
Create SOAP consumer |  | Create flow for communication from the Partner Portal in the WCF Service | 3 | 5 | 5 | PAHEH | x
Create SOAP consumer |  | Consume the client interface | 3 | 8 | 8 | PAHEH | x
Create SOAP consumer |  | Establish flow handling from A -> B | 5 | 8 | 8 | PAHEH | x
Flow Engine |  | Create flow engine that can send/resend if failing. | 8 | 13 | 13 | PAHEH | x
Flow Engine |  | Datbase Table for flow engine if needed. | 2 | 2 | 2 | JOHAN | x
|  | Estimation: | 21 | 36 | 36 |  |  | 36 | 36 | 2 | 31
Area: | Create DTO Objects matching XML creation (IN = Incomming/OUT = Outgoing)
Task |  | Description | Best case | Reel | Worst case | Assigned to
Base test project |  | Create test project for containing future tests for the project | 5 | 5 | 5 | JOHAN | x
Tilmelding 'Annullering' (IN/OUT) |  | Create the DTO entity for serializing to and from xml | 3 | 3 | 5 | JOHAN | x
Tilmelding 'Annullering' (IN/OUT) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Tilmelding 'Erstatning' (IN) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Tilmelding 'Erstatning' (IN) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Tilmelding ’Original’ (OUT) |  | Create the DTO entity for serializing to xml | 5 | 8 | 8 | JOHAN | x
Tilmelding ’Original’ (OUT) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 3 | 3 | JOHAN | x
Tilmelding og færdigmelding (OUT) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Tilmelding og færdigmelding (OUT) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Tilmelding og færdigmelding ’Erstatning’ (IN) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Tilmelding og færdigmelding ’Erstatning’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Anvisning, svar på ’Original’ (IN) |  | Create the DTO entity for serializing to xml | 5 | 5 | 8 | JOHAN | x
Anvisning, svar på ’Original’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Tilmelding afsluttet ’Original’ (IN) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Tilmelding afsluttet ’Original’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Afvisning af ’Tilmelding’ (IN) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Afvisning af ’Tilmelding’ (IN) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Færdigmelding (OUT) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Færdigmelding (OUT) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
Klar Til måler ’Original’ (OUT) |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | x
Klar Til måler ’Original’ (OUT) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
SagsInfo (?) |  | Create the DTO entity for serializing to xml | 2 | 2 | 2 | JOHAN | x
SagsInfo (?) |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN | x
|  | Estimation: | 56 | 67 | 72 |  |  | 67 | 72 | 67 | 0
Area: | Investigate
Task |  | Description | Best case | Reel | Worst case | Assigned to
Real life xml data |  | Add functionality in SW inst service for dumping xml documentation for use in flow comparison | 3 | 5 | 5 | PAHEH | x
Investigate |  | Shared entities in the XML documents, how to manage differentiating structures | 1 | 1 | 1 | JOHAN | x
Investigate |  | Schematron in workorder? What are the needs and are there any? | 0 | 0 | 0 | PAHEH | *After asking around nobody knows if we should use it, hence it will NOT be taken into account at the first version.
|  | Estimation: | 4 | 6 | 6 |  |  | 6 | 6 | 1 | 5
Area: | Incomming
Task |  | Description | Best case | Reel | Worst case | Assigned to
Error messages |  | How to send/report errors? | 5 | 8 | 8 | PAHEH | x
|  | Estimation: | 5 | 8 | 8 |  |  | 8 | 8 | 0 | 8
Area: | Outgoing
Task |  | Description | Best case | Reel | Worst case | Assigned to
Deserialization |  | Add method for deserializing (Xml string to Entity) | 3 | 3 | 5 | JOHAN | x
Deserialization |  | Add Autotest for deserialization | 2 | 2 | 2 | JOHAN | x
|  | Estimation: | 5 | 5 | 7 |  |  | 5 | 7 | 5 | 0
Area: | Tests
Task |  | Description | Best case | Reel | Worst case | Assigned to
Auto tests |  | Create Auto Test project that runs on build environment | 5 | 8 | 8
Auto tests |  | Add tests for the incomming flow
Auto tests |  | Add tests for the outgoing flow
Manual testing |  | Flow testing for the new installations flow
Manual testing |  | Flow testing for Expanding flow
Manual testing |  | Flow testiing for the Plombebrud flow
|  | Estimation: | 5 | 8 | 8 |  |  | 8 | 8 | 0 | 0
Area: | Documentation
Task |  | Description | Best case | Reel | Worst case | Assigned to
Documentation |  | Create external installation manual for customers to use when setting up/creating the clients in their end | 3 | 5 | 5
Documentation |  | Create internal installation manual/trouble shooting guides for internal personnel | 3 | 3 | 3
Documentation |  | Create developer documentation for flow/debugging/etc | 5 | 8 | 8
|  | Estimation: | 11 | 16 | 16 |  |  | 16 | 16 | 0 | 0
Area: | Security
Task |  | Description | Best case | Reel | Worst case | Assigned to
Basic Authentification |  | How to safely create Basic Authentification in a Soap Connection | 5 | 8 | 8 | PAHEH
IP whitelisting |  | Create DB table for configuration | 2 | 2 | 2 | JOHAN
IP Whitelisting |  | Create logic for checking IP address against saved addresse | 3 | 5 | 5 | PAHEH
IP whitelisting |  | Create UI for saving IP addresses for customer |  |  |  | ? | *
|  | Estimation: | 10 | 15 | 15 |  |  | 15 | 15 | 2 | 13
Area: | Core Logic (engine)
Task |  | Description | Best case | Reel | Worst case | Assigned to
Versioning |  | Create versioning in the service | 3 | 5 | 8 | PAHEH
Logging |  | Add logging functionality to the Soap interface | 5 | 5 | 5 | PAHEH
Logging |  | Add Database Log table for the logging functionality | 2 | 2 | 2 | JOHAN
Form and data header to xml |  | Outgoing flow needs headers in the messages | 2 | 3 | 3 | JOHAN
Extend DataModel |  | Extend the data model with XML codes (also in the database) | 2 | 3 | 3 | JOHAN
|  | Estimation: | 14 | 18 | 21 |  |  | 18 | 21 | 8 | 10
Area: | Logical paths
Task |  | Description | Best case | Reel | Worst case | Assigned to
Data incomming |  | Create the logic for transporting the data from the soap-handover all the way to the database | 8 | 13 | 13 | JOHAN | *
Data outgoing |  | Create the logic for transporting the data from the database to the outgoing api | 8 | 8 | 8 | JOHAN | *
Logic flow in SOAP SOAP vs REST |  | Create logical path according to the z-type received. | 3 | 5 | 5 | PAHEH
|  | Estimation: | 16 | 21 | 21 |  |  | 21 | 21 | 11 | 5
Area: | Test Environment
Task |  | Description | Best case | Reel | Worst case | Assigned to
Opsætning |  | Configuration of unknowen factors. IIS Ports etc | 8 | 8 | 13
|  | Estimation: | 8 | 8 | 13 |  |  | 8 | 13 | 8 | 0
[7 empty] | Sum: | 248 | 266
|  |  | Assigned to JOHAN: |  |  | 33 |  |  |  | 107
|  |  | Assigned to PAHEH |  |  | 11 |  |  |  |  | 101
hh