## Sheet1
PartnerPortal - WorkOrder Flow |  |  | Projekt plan
Area: | Create incomming SOAP interface for SonWin Test Environment |  |  | Estimate in story points |  |  |  |  | Avg: | Worst | SP JOHAN | SP PAHEH | DONE
Task |  | Case | Description | Best case | Reel | Worst case | Assigned to
Create SOAP WCF Service |  | 565 | Create a WCF Service Application in the existing PP GIT Repository | 3 | 3 | 5 | PAHEH | [5 empty] | 3
HttpS setup |  | 566 | Add httpS connection in the WCF service according to the configuration in the existing InstallationsBlanbket.dk interface | 3 | 8 | 8 | PAHEH | pp
Configuration of service |  | 567 | Add configuration for the binding according to existing installations blanket service | 1 | 2 | 3 | PAHEH | [5 empty] | 2
Demo project |  | 568 | Expand UI demo project for consuming and calling real xms | 2 | 8 | 3 | PAHEH | [5 empty] | 8
Build configuration |  | 571 | Find out and make the build configuration for the service to be build in build env. (Info talk with someone) | 0 | 0 | 0 | PAHEH | Skipped (deployed in azure) |  |  |  |  | 0
Deployment |  | 569 | Deploy the service in the test environment (Ports, env setup) | 8 | 8 | 13 | PAHEH | [5 empty] | 13
XML Validation |  | 907 | Implement basic SOAP Validation | 1 | 2 | 3 | PAHEH | [5 empty] | 2
Data validation |  | 908 | Implement data validation | 2 | 2 | 2 | PAHEH | [5 empty] | 2
Debug parameter |  | 909 | Add debug parameter to the REST call and the REST interface | 3 | 5 | 8 | PAHEH | [5 empty] | 5
Establish connection |  | 570 | Setup SonWin Server InstallationManagementElectricity Service for connecting with the new WFC service | 2 | 8 | 8 | PAHEH | [5 empty] | 8
|  |  | Estimation: | 25 | 46 | 53 |  |  | 46 | 53 | 3 | 29
Area: | Create outgoing SOAP API interface
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Create SOAP consumer |  | 573 | Create flow for communication from the Partner Portal in the backend api | 3 | 5 | 5 | JOHAN | [5 empty] | 5
Create SOAP consumer |  | 574 | Consume the client interface | 3 | 8 | 8 | PAHEH | [5 empty] | 8
Create SOAP consumer |  | 575 | Establish flow handling from A -> B | 5 | 8 | 8 | PAHEH | [5 empty] | 8
Flow Engine |  | 576 | Create flow engine that can send/resend if failing. | 8 | 13 | 13 | PAHEH | [5 empty] | 13
Flow Engine |  | 577 | Datbase Table for flow engine if needed. | 2 | 2 | 2 | JOHAN | [5 empty] | 2
|  |  | Estimation: | 21 | 36 | 36 |  |  | 36 | 36 | 2 | 31
Area: | Create DTO Objects matching XML creation (IN = Incomming/OUT = Outgoing)
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Base test project |  |  | Create test project for containing future tests for the project | 5 | 5 | 5 | JOHAN
Tilmelding 'Annullering' (IN/OUT) |  |  | Create the DTO entity for serializing to and from xml | 3 | 3 | 5 | JOHAN
Tilmelding 'Annullering' (IN/OUT) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Tilmelding 'Erstatning' (IN) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Tilmelding 'Erstatning' (IN) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Tilmelding ’Original’ (OUT) |  |  | Create the DTO entity for serializing to xml | 5 | 8 | 8 | JOHAN | [5 empty] | 8
Tilmelding ’Original’ (OUT) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 3 | 3 | JOHAN
Tilmelding og færdigmelding (OUT) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Tilmelding og færdigmelding (OUT) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Tilmelding og færdigmelding ’Erstatning’ (IN) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Tilmelding og færdigmelding ’Erstatning’ (IN) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Anvisning, svar på ’Original’ (IN) |  |  | Create the DTO entity for serializing to xml | 5 | 5 | 8 | JOHAN | [5 empty] | 5
Anvisning, svar på ’Original’ (IN) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Tilmelding afsluttet ’Original’ (IN) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Tilmelding afsluttet ’Original’ (IN) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Afvisning af ’Tilmelding’ (IN) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Afvisning af ’Tilmelding’ (IN) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Færdigmelding (OUT) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN
Færdigmelding (OUT) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
Klar Til måler ’Original’ (OUT) |  |  | Create the DTO entity for serializing to xml | 2 | 3 | 3 | JOHAN | [5 empty] | 3
Klar Til måler ’Original’ (OUT) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
SagsInfo (?) |  |  | Create the DTO entity for serializing to xml | 2 | 2 | 2 | JOHAN
SagsInfo (?) |  |  | Create autotest for ensuring that the generated xml will not be changed | 2 | 2 | 2 | JOHAN
|  |  | Estimation: | 56 | 67 | 72 |  |  | 67 | 72 | 67 | 0
Area: | Investigate
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Real life xml data |  | 990 | Add functionality in SW inst service for dumping xml documentation for use in flow comparison | 3 | 5 | 5 | PAHEH | [5 empty] | 5
Real life xml data |  | 1050 | Harvest the xml data by following the various flows in the installations blanket.dk | 3 | 5 | 8 | PAHEH/HALINA | [5 empty] | 5
Company references |  |  | Are the binding between the grid company and supplier allready made? | 1 | 2 | 2 | PAHEH
Cleanup |  | 1181 | Investigate if ipwhilelisting should be handled by azure rather than the wcf, logging should always just be to file. (remove code acording to this) | 3 | 3 | 3 | PAHEH | [5 empty] | 3
Investigate |  |  | Shared entities in the XML documents, how to manage differentiating structures | 1 | 1 | 1 | JOHAN | [5 empty] | 1
Investigate |  | 736 | Investigate the possebility of using .,net CORE in WCF Service | 3 | 5 | 8 | PAHEH | NOPE |  |  |  |  | 5
Investigate |  |  | Schematron in workorder? What are the needs and are there any? | 0 | 0 | 0 | PAHEH | *After asking around nobody knows if we should use it, hence it will NOT be taken into account at the first version. |  |  |  |  | 0
|  |  | Estimation: | 14 | 21 | 27 |  |  | 21 | 27 | 1 | 5
Area: | Incomming
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Error messages |  | 607 | How to send/report errors? | 5 | 8 | 8 | PAHEH | [5 empty] | 8
|  |  | Estimation: | 5 | 8 | 8 |  |  | 8 | 8 | 0 | 8
Area: | Outgoing
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Xml processor |  | 1019 | Create Outgoing XML Processor (serialization, validation, SOAP) | 8 | 8 | 8 | JOHAN | [5 empty] | 8
Deserialization |  |  | Add method for deserializing (Xml string to Entity) | 3 | 3 | 5 | JOHAN | [5 empty] | 3
Deserialization |  |  | Add Autotest for deserialization | 2 | 2 | 2 | JOHAN
|  |  | Estimation: | 13 | 13 | 15 |  |  | 13 | 15 | 5 | 0
Area: | Tests
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Auto tests |  | 637 | Create Auto Test project for the wcf service | 5 | 5 | 8 | PAHEH | Local tests |  |  |  |  | 5
Auto tests |  | 638 | Add tests for the incomming flow
Auto tests |  | 639 | Add tests for the outgoing flow
Manual testing |  | 640 | Manual Flow testing
|  |  | Estimation: | 5 | 5 | 8 |  |  | 5 | 8 | 0 | 0
Area: | Documentation
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Documentation |  |  | Create external installation manual for customers to use when setting up/creating the clients in their end | 3 | 5 | 5
Documentation |  |  | Create internal installation manual/trouble shooting guides for internal personnel | 3 | 3 | 3
Documentation |  |  | Create developer documentation for flow/debugging/etc | 5 | 13 | 13
|  |  | Estimation: | 11 | 21 | 21 |  |  | 21 | 21 | 0 | 0
Area: | Security
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Basic Authentification |  |  | How to safely create Basic Authentification in a Soap Connection | 5 | 8 | 8 | PAHEH | pp
Brute Force Safety |  |  | Make logic in order to prevent brute force attacs | 5 | 8 | 8 |  | pp
IP whitelisting |  |  | Create DB table for configuration | 2 | 2 | 2 | JOHAN | [5 empty] | 2
IP Whitelisting |  |  | Create logic for checking IP address against saved addresse | 3 | 5 | 5 | PAHEH | Missing fetch from api but logic is ready from file |  |  |  |  | 5
Service of denial safety |  |  | Make logic in order to prevent denial of service | 5 | 8 | 8 | PAHEH | pp
IP whitelisting |  |  | Create UI for saving IP addresses for customer |  |  |  | ?
|  |  | Estimation: | 20 | 31 | 31 |  |  | 31 | 31 | 2 | 13
Area: | Core Logic (engine)
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Versioning |  | 624 | Create versioning in the api | 3 | 5 | 8 | JOHAN
Logging |  | 625 | Add logging functionality to the Soap interface | 5 | 5 | 5 | PAHEH | [5 empty] | 5
XML Logging |  | 626 | Add Database Log table for the logging functionality | 2 | 2 | 2 | JOHAN | Skipped for wcf |  |  |  |  | 2
XML Logging |  | 627 | Add logging functionality for writing to the database | 3 | 5 | 8 | JOHAN | Skipped for wcf |  |  |  |  | 8
Debug Logging |  | 1061 | Create shared project. | 5 | 5 | 5 | PAHEH
Form and data header to xml |  | 628 | Outgoing flow needs headers in the messages | 2 | 3 | 3 | JOHAN | [5 empty] | 3
New api interface |  | 734 | Add new api project for intercepting comm from SOAP interface | 2 | 5 | 8 | JOHAN | [5 empty] | 5
WCF -> Api |  | 876 | Connect to the new Api from the wcf service and send data | 5 | 8 | 13 | PAHEH | [5 empty] | 8
Extend DataModel |  | 629 | Extend the data model with XML codes (also in the database) | 2 | 3 | 3 | JOHAN
|  |  | Estimation: | 29 | 41 | 55 |  |  | 41 | 55 | 8 | 10
Area: | Logical paths
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Data incomming |  |  | Create the logic for transporting the data from the soap-handover all the way to the database | 8 | 13 | 13 | JOHAN
Data outgoing |  |  | Create the logic for transporting the data from the database to the outgoing api | 8 | 8 | 8 | JOHAN
Logic flow in SOAP SOAP vs REST |  |  | Create logical path according to the z-type received. | 3 | 5 | 5 | PAHEH
|  |  | Estimation: | 16 | 21 | 21 |  |  | 21 | 21 | 11 | 5
Area: | Test Environment
Task |  |  | Description | Best case | Reel | Worst case | Assigned to
Opsætning |  |  | Configuration of unknown factors. IIS Ports etc | 8 | 8 | 13 | PAHEH | [5 empty] | 13
|  |  | Estimation: | 8 | 8 | 13 |  |  | 8 | 13 | 8 | 0
[8 empty] | Sum: | 318 | 360
|  |  |  | Assigned to JOHAN: |  |  | 38 |  |  |  | 107
|  |  |  | Assigned to PAHEH |  |  | 18 |  |  |  |  | 101
|  |  |  | Done: | [8 empty] | 189
|  |  |  | Missing: |  |  |  |  | 129 | 171